## Project Planner
SKYJoB Gantt Planner
Project began on 3/17/2017. Each period is equal to 1 day. | [8 empty] | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Proposal | 1 | 21 | 1 | 21 | 100%
Remote Mapping | 8 | 7 | 8 | 7 | 100%
Movement Control | 15 | 7 | 15 | 7 | 100%
Parallel Maneuver | 15 | 7 | 15 | 7 | 100%
Perpendicular Maneuver | 15 | 7 | 15 | 7 | 100%
Autonomous Maneuver | 15 | 14 | 15 | 14 | 100%
Control Interupt | 22 | 7 | 22 | 7 | 100%
Sonar | 22 | 7 | 22 | 7 | 100%
Oral Presentation | 22 | 7 | 22 | 7 | 100%
Final Report | 29 | 7 | 29 | 7 | 100%